## Instructions
RISK MANAGEMENT LOG
Column | Instructions For Completing This Document
Complete the Project Name, NC, Project Manager Name, and Project Description fields
For each risk identified, complete the following:
A | ID: A unique ID number used to identify the risk in the risk tracking log.
B | Current Status: This column should be populated with the risk's current status. o Open: The risk is currently open but is not yet an issue. o Closed: The risk is no longer considered an active project threat and can be closed with or without resolution.
C | Risk Impact: This column should be populated with the potential impact of the risk if it did become a project issue. Valid options include the following: High, Medium, Low. These are defined as follows: o High: Risk that has the potential to greatly impact project cost, project schedule or performance. o Medium: Risk that has the potential to slightly impact project cost, project schedule or performance. o Low: Risk that has relatively little impact on cost, schedule or performance.
D | Probability of Occurrence: This column should be populated with the estimated probability that the risk will at some point become a project issue.
E | Risk Map: This is a calculated field based on the values selected for both Risk Impact and Probability of Occurrence. o Green: LL (Low Probability, Low Impact), LM (Low Probability, Medium Impact), ML (Medium Probability, Low Impact) o Yellow: LH (Low Probability, High Impact), MM (Medium Probability, Medium Impact), HL (High Probability, Low Impact) o Red: MH (Medium Probability, High Impact), HM (High Probability Medium Impact), HH (High Probability, High Impact)
F | Risk Description: This column should be populated with a description of the risk.
G | Project Impact: This column should be populated with a description of the potential project impact as a result of the risk.
H | Risk Area: This column should be populated with the appropriate risk area.
I | Symptoms: This column should be populated with the symptoms of risk that may eventually lead to the execution of a risk contingency plan.
J | Trigger: This column should be populated with the triggers that would indicate the requirement to execute contingency plans.
K | Risk Response Strategy: This column should be populated with the preferred risk response strategy.
L | Response Strategy: This column should be populated an appropriate response strategy to prevent the risk from becoming an issue.
M | Contingency Plan: This column should be populated with a description of the risk contingency plan.
Column | Instructions For Changing the Contents of Drop-Down Menus
C, D, H | Highlight the cell of which you wish to change the content of the drop down menu. From the file menu click "Data" -> "Validation" and change the content of the source field
Column | Instructions For Filtering Data
Any | Highlight the header of the cell you wish to filter data on From the file menu click "Date" -> "Filter" ->"Auto Filter" Then select your filter criteria from the drop down menu that appears on your header cell

## Risk_Tracking_Log
RISK MANAGEMENT LOG | [7 empty] | RISK MANAGEMENT LOG
Project Name: |  |  | Foodies |  |  |  |  | Project Name: | Foodies
Project Manager Name: |  |  | Monica Atef |  |  |  |  | Project Manager Name: | Monica Atef
Project Description: |  |  | our website will help the user to connect and reach all the restaurants in his/her area and make it easier for him to make orders |  |  |  |  | Project Description: | our website will help the user to connect and reach all the restaurants in his/her area and make it easier for him to make orders
ID | Current Status | Risk Impact | Probability of Occurrence | Risk Map | Risk Description | Project Impact | Risk Area | Symptoms | Triggers | Risk Response Strategy | Response Strategy | Contingency Plan
RI_0 | Open | High | Low | Yellow | Current project skill set may not be adequate to complete all project work. The current development team has been working in a desktop and mobile development, and the current requirements are for a web base development. The project schedule would require 500 development hours of a skilled web developer, and approximately 900 to 1000 if we retrain our current resources. | If required skills are not identified or obtained, project schedule may slip and possibly restrict the accomplishment of project goals. | Project Resources Budget Schedule | Schedule approaches the required start date with no identification of required skill sets. | Two weeks prior to scheduled start date if no resource is identified with required skill set implement contingency plan. | Mitigation | Find internal resource that meets required skill set or train existing resources on web applications developments. | Find resource that meets required skill set through external hiring sources.
RI_1 | Open | Medium | Medium | Yellow | Current developers number is limited if any developer has an emergency situation or can't continue the project for any reason the project timeline will be affected. | If any one from developers team left project schedule may slip and possibly restrict the accomplishment of project goals. | Project Resources Budget Schedule | Required team members' numbers have to be assigned according to estimation with adding one or more members that may be unavailable. | Two weeks prior to scheduled start date if the number of team members is not identified with required skill set implement contingency plan. | Mitigation | Find internal resource that meets required skill and be available through project timeline or increasing work load on current team members. | open hiring internal or external for the team or searching for a freelancer to complete the job.
RI_2 | Open | Low | Low | Green | License for tools or OS may be expired and have to be renewed. | If the tools license is expired some teams can't continue their job and the project schedule may slip and possibly restrict the accomplishment of project goals. | Budget Schedule | The license end date has to be tracked by checking it or an alarm will appear. | A warning message of ending the license will appear to the team. | Avoidance | The IT support team will renew the licenses. | Using another open source tool.
RI_3 | Open | High | Medium | Red | The wrong estimation of the project budget, the project budget is not enough to end the project. | If the budget is not enough for the project the project won't release with all the agreed features. | Life-cycle Costs Budget | There are a number of features are not implemented yet and the budget is lower than the expected budget in the plan. | There was at least 5 feature not implemented yet and the budget is lower than 30%. | Mitigation | Ask the customer if he wants to increase the budget to complete all features or release with current features. | The current team will work overtime to end all features.
RI_4 | Open | High | Medium | Red | The wrong estimation of the project schedule the project timeline is not enough to end the project. | If there was a deviation of project schedule the project won't release with all the agreed features. | Schedule | Having technical debt or there a delay in tasks delivery. | There were two weeks for delivery and all features were not closed yet. | Mitigation | The current team will work overtime to end all features. | find someone internal that can help the team or searching for a freelancer to complete the job.
RI_5 | Open | High | Low | Yellow | Client doesn't know what he really needs | If the client really doesn't have a clear vision this will have a negative impact on the timeframe and the budget | Project Resources Budget Schedule | Long delays, lots of changes, extra expenses. | Customer is not sure about the information which he provides us with.beside that he may be hestiant. | Mitigation | the business analysist will have an interview with him to discuss more about his needs | the team will search and collect data from similar pervious projects and then use this information in the current project
RI_6 | Open | High | Medium | Red | Unavailability of stockholder | if the client/stakeholder is not avaliable this will cause some blocks in the development | Project Resources Budget Schedule | Some Requirements may be not met as the customer needed After a lot of time there may exist a major change in the project | The team wants some clarifications and some validation on the work and he can't communicate /reach the customer | Mitigation | Determine which stakeholder will have an influence on the current part you are working on it Always Try to have a weekly meeting with them as to communicate with them the progress takes their feedback in early stages | the team will search and collect data from similar pervious projects and then use this information in the current project
RI_7 | Open | Medium | High | Red | In the middle of the project, client will say that he won't continue | the project will stop | Project Resources Budget Schedule | Wastes time and expenses | the customer found a cheaper company | Avoidance | Discuss with the client that cheaper doesn't mean better or faster. To estimate the Cost with respect to the size and the scope of the current project so that the cost is not too high that makes the customer search for alternatives | The advance payment and/or contractual penalty placed in the contract.
RI_8
RI_9
RI_10
Note on A5: ====== ID#AAAAYDWXJAY eze3 (2022-04-15 18:42:52) • ID: A unique ID number used to identify the risk in the risk management log.
Note on B5: ====== ID#AAAAYDWXJAk eze3 (2022-04-15 18:42:52) • Current Status: This column should be populated with the risk's current status. o Open: The risk is currently open but is not yet an issue. o Closed: The risk is no longer considered an active project threat and can be closed with or without resolution.
Note on C5: ====== ID#AAAAYDWXJAo eze3 (2022-04-15 18:42:52) • Risk Impact: This column should be populated with the potential impact of the risk if it did become a project issue. Valid options include the following: High, Medium, Low. These are defined as follows: o High: Risk that has the potential to greatly impact project cost, project schedule or performance. o Medium: Risk that has the potential to slightly impact project cost, project schedule or performance. o Low: Risk that has relatively little impact on cost, schedule or performance.
Note on D5: ====== ID#AAAAYDWXJA4 eze3 (2022-04-15 18:42:52) • Probability of Occurrence: This column should be populated with the estimated probability that the risk will at some point become a project issue. o High: Greater than 70% probability of occurrence. o Medium: Between 30% and 70% probability of occurrence. o Low: Below 30% probability of occurrence.
Note on E5: ====== ID#AAAAYDWXJAc e (2022-04-15 18:42:52) • Risk Map: This is a calculated field based on the values selected for both Risk Impact and Probability of Occurrence. o Green: LL (Low Probability, Low Impact), LM (Low Probability, Medium Impact), ML (Medium Probability, Low Impact) o Yellow: LH (Low Probability, High Impact), MM (Medium Probability, Medium Impact), HL (High Probability, Low Impact) o Red: MH (Medium Probability, High Impact), HM (High Probability Medium Impact), HH (High Probability, High Impact)
Note on F5: ====== ID#AAAAYDWXJAg eze3 (2022-04-15 18:42:52) • Risk Description: This column should be populated with a description of the risk.
Note on G5: ====== ID#AAAAYDWXJAM e (2022-04-15 18:42:52) • Project Impact: This column should be populated with a description of the potential project impact as a result of the risk.
Note on H5: ====== ID#AAAAYDWXJA8 eze3 (2022-04-15 18:42:52) • Risk Area: This column should be populated with the appropriate risk area.
Note on I5: ====== ID#AAAAYDWXJA0 e (2022-04-15 18:42:52) • Symptoms: This column should be populated with the symptoms of risk that may eventually lead to the execution of a risk contingency plan.
Note on J5: ====== ID#AAAAYDWXJAU e (2022-04-15 18:42:52) • Triggers: This column should be populated with the triggers that would indicate the requirement to execute contingency plans.
Note on K5: ====== ID#AAAAYDWXJAQ e (2022-04-15 18:42:52) Risk Response Strategy: This column should be populated with the preferred risk response strategy.
Note on L5: ====== ID#AAAAYDWXJAw eze3 (2022-04-15 18:42:52) • ResponseStrategy: This column should be populated an appropriate response strategy to prevent the risk from becoming an issue.
Note on M5: ====== ID#AAAAYDWXJAs e (2022-04-15 18:42:52) • Contingency Plan: This column should be populated with a description of the risk contingency plan.

## DropDown_Elements (hidden)
Risk Area
Schedule
Initial Costs
Life-cycle Costs
Technical Obsolescence
Feasibility
Reliability of Systems
Dependencies/Interoperability
Surety Considerations
Future Procurements
Project Management
Overall Project Failure
Organizational/Change Management
Business
Data/Information
Technology
Strategic
Security
Privacy
Project Resources