## PMP_Review
Review ID | Raised By | Assigned To | Issue Date | Issue | Status | Approved By | Closed date | Comments From Doc. Author | Comments From Reviewer
F_REVIEW_PMP_V1.0_001 | Marina Hatem | Aml Nasser | 2022-04-13 | In 3.1, please provide the specific section of Quality Control you are following in ISTQB | Closed | Marina Hatem | 2022-04-15
F_REVIEW_PMP_V1.0_002 | Marina Hatem | Aml Nasser | 2022-04-13 | Please provide the project name at the top of all pages. | Closed | Marina Hatem | 2022-04-15
F_REVIEW_PMP_V1.0_003 | Marina Hatem | Aml Nasser | 2022-04-13 | Please provide a definition for the following terms in Appendix C: "Dark Data" , "Email Bounce" , "Gap Analysis". | Closed | Marina Hatem | 2022-04-15
F_REVIEW_PMP_V1.0_004 | Marina Hatem | Aml Nasser | 2022-04-13 | In section 3.3, There are clear copied text. For example: "Set your quality standards. Decide which quality standards to focus on. . Get feedback." Please adjust it. | Closed | Marina Hatem | 2022-04-15
F_REVIEW_PMP_V1.0_005 | Marina Hatem | Aml Nasser | 2022-04-13 | Please remove the unnecessary blue text in all the sheet. | Closed | Marina Hatem | 2022-04-15
F_REVIEW_PMP_V1.0_006 | Marina Hatem | Aml Nasser | 2022-04-13 | Please provide a definition for the ISTQB in Appendix B | Closed | Marina Hatem | 2022-04-15
F_REVIEW_PMP_V1.1_007 | Hagar EL-Sayed | Aml Nasser | 2022-04-27 | In our vision in page 3 we need to add our industry in the description "food delivery" | Closed | Hagar EL-Sayed | 2022-04-29
F_REVIEW_PMP_V1.1_009 | Hagar EL-Sayed | Aml Nasser | 2022-04-27 | In page 3 unique solution Cancel the nearby restaurants feature | Closed | Hagar EL-Sayed | 2022-04-29
F_REVIEW_PMP_V1.1_010 | Hagar EL-Sayed | Aml Nasser | 2022-04-27 | In assumptions section in page 4 we need to add a confirmation page or message at least for orders | Closed | Hagar EL-Sayed | 2022-04-29 | No Need it will be Fully descriptive at SRS document + it's not an assumption | Agreed
F_REVIEW_PMP_V1.1_011 | Hagar EL-Sayed | Aml Nasser | 2022-04-27 | In 3.3 Dependencies add that we are using some agile methodologies in reviewing and daily meetings | Closed | Hagar EL-Sayed | 2022-04-29
F_REVIEW_PMP_V1.1_012 | Hagar EL-Sayed | Aml Nasser | 2022-04-27 | In 3.1 Milestones update the second week plan in the Schedule and in page 7 update Screenshot for Schedule | Closed | Hagar EL-Sayed | 2022-04-29
F_REVIEW_PMP_V1.1_013 | Hagar EL-Sayed | Aml Nasser | 2022-04-27 | In 6.1 Communication Matrix the customer meeting row in the audience remove the product owner role | Closed | Hagar EL-Sayed | 2022-04-29
F_REVIEW_PMP_V1.1_014 | Hagar EL-Sayed | Aml Nasser | 2022-04-27 | In page 11 the versions of the mentioned files should be updated when changed | Closed | Hagar EL-Sayed | 2022-04-29
F_REVIEW_PMP_V1.1_015 | Hager Hany | Aml Nasser | 2022-04-29 | CI List should be included in PMP document file there is no need to be separate | Closed | Hager Hany | 2022-04-29

## Options (hidden)
Open
Closed
In Progress
Need Approval

## Risk_Managment_Plan_Review
Review ID | Raised By | Assigned To | Issue Date | Issue | Status | Closed By | Closed date | Comments From Doc. Author | Comments From Reviewer
F_REVIEW_RMP_V1.0_001 | Hagar EL-Sayed | Aml Nasser | 2022-04-27 | In 1.1 the purpose of risk management plan in the risk definition it is written as "have a positive or negative " we should eliminate "positive". | Closed | Hagar EL-Sayed | 2022-04-29
F_REVIEW_RMP_V1.0_002 | Hagar EL-Sayed | Aml Nasser | 2022-04-27 | IN 1.1 the purpose of risk management plan in the "Internet Banking System" part should be modified | Closed | Hagar EL-Sayed | 2022-04-29
F_REVIEW_RMP_V1.0_003 | Hagar EL-Sayed | Aml Nasser | 2022-04-27 | In 2.1 the process <project manager or other designee> a specific role should replace the brackets | Closed | Hagar EL-Sayed | 2022-04-29
F_REVIEW_RMP_V1.0_004 | Hagar EL-Sayed | Aml Nasser | 2022-04-27 | In 2.2 Risk identification "will be stored electronically in the project library located at Risk_Management_Log.xls." should be checked for the actual storage place. | Closed | Hagar EL-Sayed | 2022-04-29 | No need To specify Location, will mention the location at the appendix Page | Agreed
F_REVIEW_RMP_V1.0_005 | Hagar EL-Sayed | Aml Nasser | 2022-04-27 | In page 6 mention the people who need to sign | Closed | Hagar EL-Sayed | 2022-04-29
F_REVIEW_RMP_V1.0_006 | Hagar EL-Sayed | Aml Nasser | 2022-04-27 | In page 7 in the appendix mention the place for Risk log | Closed | Hagar EL-Sayed | 2022-04-29

## WireFrame_Review
Review ID | Raised By | Assigned To | Issue Date | Issue | Status | Approved By | Closed date | Comments From Doc. Author | Comments From Reviewer
F_REVIEW_WFrame_V1.0_001 | Marina | Hagar El Sayed | 2022-05-05 | The nav bar contains unnecessary tabs that are not mentioned in the requirements. Those tabs are: "Destination", "Category, "Tours", "Holidays", "About us", "Branches", "Contact us". Please remove them. | Closed |  | 2022-05-06
F_REVIEW_WFrame_V1.0_002 | Marina | Hagar El Sayed | 2022-05-05 | After closing review "F_REVIEW_WFrame_V1.0_001", add the following to the nav bar from left to right: "Offers", "circle with user's picture", "Sign out button". NOTE: This is the nav bar after the user signs in. "Register and "Sign out" buttons will take place the "Sign out" button in the nav bar if the user has not registered or signed in. | Closed |  | 2022-05-06
F_REVIEW_WFrame_V1.0_003 | Marina | Hagar El Sayed | 2022-05-05 | In the Login page wireframe, Remove "Forgot password?" hyperlink because it is not mentioned in the Requirements. | closed
F_REVIEW_WFrame_V1.0_004 | Marina | Hagar El Sayed | 2022-05-05 | In the menu items page, please make sure to update the nav bar as the one mentioned in review "F_REVIEW_WFrame_V1.0_002". | Closed |  | 2022-05-06
F_REVIEW_WFrame_V1.0_005 | Marina | Hagar El Sayed | 2022-05-05 | In the menu items page, please elaborate to the customer the '-' button meaning as you did with the '+' button. | Closed |  | 2022-05-06
F_REVIEW_WFrame_V1.0_006 | Marina | Hagar El Sayed | 2022-05-05 | In the menu items page, there is a button at the button right of the page that has no words and is not needed in the reguirements. Please remove it. | Closed |  | 2022-05-06
F_REVIEW_WFrame_V1.0_007 | Marina | Hagar El Sayed | 2022-05-05 | In the order confirmation page, please make sure to update the nav bar as the one mentioned in review "F_REVIEW_WFrame_V1.0_002". | closed |  | 2022-05-06
F_REVIEW_WFrame_V1.0_008 | Marina | Hagar El Sayed | 2022-05-05 | In the order confirmation page, remove the button that says "Apply your point's discount" as it is not mentioned in the requirements. | Closed |  | 2022-05-06
F_REVIEW_WFrame_V1.0_009 | Marina | Hagar El Sayed | 2022-05-05 | In the offers page, The loyalty points must take the first horizontal card in the page. | Closed |  | 2022-05-06
F_REVIEW_WFrame_V1.0_010 | Marina | Hagar El Sayed | 2022-05-05 | In the offers page, The Restraunts offers must be beneath the loyalty points. Each restraunt offer must take a card alone horizontaly with "use" button in each one. | Closed |  | 2022-05-06
F_REVIEW_WFrame_V1.0_011 | Marina | Hagar El Sayed | 2022-05-05 | In the Home page, please make sure to update the nav bar as the one mentioned in review "F_REVIEW_WFrame_V1.0_002". | Closed |  | 2022-05-06
F_REVIEW_WFrame_V1.0_012 | Marina | Hagar El Sayed | 2022-05-05 | In the Home page, please change "Restraunt menu" title to "Foodies' Restraunts" as this is the page that contains the restraunts themselves not the restraunt menus. | Closed |  | 2022-05-06
F_REVIEW_WFrame_V1.0_013 | Noura | Hagar El Sayed | 2022-05-08 | remove sign out from home page | Closed |  | 2022-05-09
F_REVIEW_WFrame_V1.0_014 | Noura | Hagar El Sayed | 2022-05-08 | missed page ( page that has a summary of the order. There will be two buttons: “Confirm” and “Cancel”) | Closed |  | 2022-05-09
F_REVIEW_WFrame_V1.0_015 | Noura | Hagar El Sayed | 2022-05-08 | Add menu item page ---> remove the (add item) button | Closed |  | 2022-05-09
F_REVIEW_WFrame_V1.0_016 | Noura | Hagar El Sayed | 2022-05-08 | Add offer page replace(Add menu item) with Add offer | closed |  | 2022-05-09
F_REVIEW_WFrame_V1.0_017 | Noura | Hagar El Sayed | 2022-05-08 | Add offer page ---> remove the add item button | closed |  | 2022-05-09
F_REVIEW_AddAdmin_001 | Noura | Hagar Nasser | 13/5 | replace useremail with email(wirefram) | open
F_REVIEW_AddUser_001 | Noura | Hagar Nasser | 13/5 | replace useremail with email(wirefram) | open

## Implementation_Review
Review ID | Raised By | Assigned To | Issue Date | Issue | Status | Approved By | Closed date | Comments From Doc. Author | Comments From Reviewer
F_REVIEW_register_001 | Noura | Marina | 13/5 | according srs and sequence all error messages must be appear after user click "register " button | open
F_REVIEW_register_002 | Noura | Marina | 13/5 | fullname&username accept numbers | open
F_REVIEW_register_003 | Noura | Marina | 13/5 | phone number accept characters | open
F_REVIEW_register_003 | Noura | Marina | 13/5 | Already a member? LogIn must be replace with “Have an account? Login here”. | open
F_REVIEW_login_001 | Noura | Marina | 13/5 | username accept numbers must be characters only so an error message will appear saying that “Invalid username or password”after click login | open
F_REVIEW_AddAdmin_001 | Noura | Marina | 13/5 | check vaildation of all fields in add admin page | open
F_REVIEW_AddAdmin_002 | Noura | Marina | 13/5 | Add Admin button replace with Add | open
F_REVIEW_AddUser_001 | Noura | Marina | 13/5 | Add User button replace with Add | open
F_REVIEW_AddUser_002 | Noura | Marina | 13/5 | check vaildation of all fields in add admin page | open

## SRS_Review
Review ID | Raised By | Assigned To | Issue Date | Issue | Status | Approved By | Closed date | Comments From Doc. Author | Comments From Reviewer
F_REVIEW_SRS_V1.0_001 | Hager Hany | Marina&Noura | 2022-04-13 | in section 3.11.3 field constrantions the last one must be phone number not full name | Closed | Hager Hany | 2022-04-15
F_REVIEW_SRS_V1.0_002 | Hager Hany | Marina&Noura | 2022-04-13 | there is a missing admin function which is update user | Closed | Hager Hany | 2022-04-15
F_REVIEW_SRS_V1.0_003 | Hager Hany | Marina&Noura | 2022-04-13 | there is a issue in the numbering starts from 3.15 subtitles till the end of the section 3 | Closed | Hager Hany | 2022-04-15
F_REVIEW_SRS_V1.0_004 | Hager Hany | Marina&Noura | 2022-04-13 | there is a issue in 3.16 in functional requirments it doesn't match the actual requirment fo adding an admin | Closed | Hager Hany | 2022-04-15
F_REVIEW_SRS_V1.0_005 | Hager Hany | Marina&Noura | 2022-04-13 | the usage of the admin and user keywords interchangably is not applicable so please revise the functionality of the adim as whole | Closed | Hager Hany | 2022-04-15
F_REVIEW_SRS_V1.0_006 | Hager Hany | Marina&Noura | 2022-04-13 | the add item /delete /update item is not in our scope | Closed | Hager Hany | 2022-04-15
F_REVIEW_SRS_V1.0_007 | Hager Hany | Marina&Noura | 2022-04-13 | section 3.22 has a conflict topic | Closed | Hager Hany | 2022-04-15
F_REVIEW_SRS_V1.0_008 | Hager Hany | Marina&Noura | 2022-04-13 | missing admin function which is update add delete menu | Closed | Hager Hany | 2022-04-15
F_REVIEW_SRS_V1.0_009 | Hager Hany | Marina&Noura | 2022-04-13 | in section 5.3 the authorization some functions of admin is forgotten which is add/update/delet menus | Closed | Hager Hany | 2022-04-15
F_REVIEW_SRS_V1.0_010 | Hager Hany | Marina&Noura | 2022-04-13 | in section 5.1 I think we need to remove the part of the delay of 5 seconds | Closed | Hager Hany | 2022-04-15
F_REVIEW_SRS_V1.0_011 | Hager Hany | Marina&Noura | 2022-04-13 | in section 5.4 we need to express the avialibilty in nines we can review this link to help https://www.blameless.com/sre/availability-maintainability-reliability-whats-the-difference | Closed | Hager Hany | 2022-04-15
F_REVIEW_SRS_V1.0_012 | Hagar EL-Sayed | Marina&Noura | 2022-04-13 | in the first page the prepared by section font and arrage of the members names is not right | Closed | Hagar EL-Sayed | 2022-04-15
F_REVIEW_SRS_V1.0_013 | Hagar EL-Sayed | Marina&Noura | 2022-04-13 | in section 1.1, the Purpose there is a problem in the sequence espcially here "The customers can get their order delivered" and then the rest | Closed | Hagar EL-Sayed | 2022-04-15
F_REVIEW_SRS_V1.0_014 | Hagar EL-Sayed | Marina&Noura | 2022-04-14 | in section 1.2 , it is better to mention that changing the content is called "tailoring" | Closed | Hagar EL-Sayed | 2022-04-15
F_REVIEW_SRS_V1.0_015 | Hagar EL-Sayed | Marina&Noura | 2022-04-15 | in section 1.4 the last sentence "based on ….." it needs declaration. | Closed | Hagar EL-Sayed | 2022-04-15
F_REVIEW_SRS_V1.0_016 | Hagar EL-Sayed | Marina&Noura | 2022-04-15 | in section 2.5 it is recommended to specify how the system is going to know the near by restaurants is it by using the GPS or the user insert the required place or any other methods | Closed | Hagar EL-Sayed | 2022-04-15
F_REVIEW_SRS_V1.0_017 | Hagar EL-Sayed | Marina&Noura | 2022-04-15 | in section 3.2 there is a missing error message if the user insert a wrong data | Closed | Hagar EL-Sayed | 2022-04-15
F_REVIEW_SRS_V1.0_018 | Hagar EL-Sayed | Marina&Noura | 2022-04-15 | in section 3.6 there are missing steps what happen after the user "view the restaurant’s menu" | Closed | Hagar EL-Sayed | 2022-04-15
F_REVIEW_SRS_V1.0_019 | Hagar EL-Sayed | Marina&Noura | 2022-04-15 | in section 3.6.3, REQ-2 the user has to select the restaurant to" View their menu then choose te meal". | Closed | Hagar EL-Sayed | 2022-04-15

## Sequence_Diagrams_Review
Review ID | Raised By | Assigned To | Issue Date | Issue | Status | Approved By | Closed date | Comments From Doc. Author | Comments From Reviewer
F_REVIEW_Sequence_V1.0_001 | Noura | Hagar Hany | 2022-04-29 | absence of invalid case (bad sequence) in all sequence diagrams for admin features | Closed | Noura | 2022-04-29 | is not an issue the sequence diagram is done for the happy scenarios only
F_REVIEW_Sequence_V1.0_002 | Noura | Hagar Hany | 2022-04-29 | in 3.4 search sequence diagaram (users function) bad sequence :in case restaurant name that is not available System reapones “Restaurant not found” | Closed | Noura | 2022-04-29 | is not an issue the sequence diagram is done for the happy scenarios only

## Audit_Review
Review ID | Document | Raised By | Assigned To | Issue Date | Note | Issue | Status | Approved By | Closed date | Comments From Doc. Author | Comments From Reviewer
F_REVIEW_Audit_V1.0_001 | PMP | Eng. Mohamed Hassan | Whole Team | 2022-04-21 | General for all teams | Need CI List for Naming | Need Approval
F_REVIEW_Audit_V1.0_002 | RTM | Eng. Mohamed Hassan | Whole Team | 2022-04-21 | General for all teams | Need RTM | Need Approval
F_REVIEW_Audit_V1.0_003 | GitHub | Eng. Mohamed Hassan | Whole Team | 2022-04-21 | General for all teams | Consistency of Dates between Dev. and Master branch | Need Approval
F_REVIEW_Audit_V1.0_004 | General | Eng. Mohamed Hassan | Whole Team | 2022-04-21 | General for all teams | The Project end date is not specified yet as we can drop week in between (mention that project duration is 5 weeks without any dates) | In Progress |  |  |  | As per Eng. Amr request add Finish-date of the project in PMP and it can be shifted.
F_REVIEW_Audit_V1.0_005 | General | Eng. Mohamed Hassan | Whole Team | 2022-04-21 | General for all teams | Documents Version | Need Approval
F_REVIEW_Audit_V1.0_006 | Wireframe | Eng. Mohamed Hassan | Hagar EL-Sayed | 2022-04-21 | Our Team | Wireframe is not matched with SRS | Need Approval
F_REVIEW_Audit_V1.0_007 | SRS | Eng. Mohamed Hassan | Noura/Marina | 2022-04-21 | Our Team | SRS (ID is required) | Need Approval
F_REVIEW_Audit_V1.0_008 | SRS | Eng. Mohamed Hassan | Noura/Marina | 2022-04-21 | Our Team | SRS( give more details for each Requirement) | Need Approval
F_REVIEW_Audit_V1.0_009 | PMP | Eng. Amr Helal | Aml Nasser | 2022-05-05 | Our Team | In Section 1.3 Assumptions and Constraints -Assumption (add Log in and Tracking Order Pages) is not an assumption and customer wouldn't care about them - Constraints should be more clear for System used and Admin features | Closed | Eng. Amr Helal | 2022-05-05
F_REVIEW_Audit_V1.0_010 | PMP | Eng. Amr Helal | Aml Nasser | 2022-05-05 | Our Team | No revision history Table to show versions date | Closed | Eng. Amr Helal | 2022-05-05
F_REVIEW_Audit_V1.0_011 | PMP | Eng. Amr Helal | Aml Nasser | 2022-05-05 | Our Team | RASI chart what is the difference between accountable and responsible | Closed | Eng. Amr Helal | 2022-05-05 | The different is Responsible for executing the work on this particular task Accountable is the person who will be responsible for ensuring that the task is done properly | Agreed that we will use Approval instead of Accountable
F_REVIEW_Audit_V1.0_012 | PMP | Eng. Amr Helal | Aml Nasser | 2022-05-05 | Our Team | Milestone 3 is assumed and it is not correct | Closed | Eng. Amr Helal | 2022-05-05
F_REVIEW_Audit_V1.0_013 | PMP | Eng. Amr Helal | Aml Nasser | 2022-05-05 | Our Team | Dependency section it is better to be done via drawing | Closed | Eng. Amr Helal | 2022-05-05
F_REVIEW_Audit_V1.0_014 | PMP | Eng. Amr Helal | Aml Nasser | 2022-05-05 | Our Team | For external references please mention the path where the document is stored | Closed | Eng. Amr Helal | 2022-05-05 | It’s mentioned in (APPENDIX A: REFERENCES) Section the location of each external reference Should I mention it in each section | Agreed that we will mention the location Link in each section and accumulate all lonks in (APPENDIX A: REFERENCES) Section
F_REVIEW_Audit_V1.0_015 | PMP | Eng. Amr Helal | Aml Nasser | 2022-05-05 | Our Team | Conf. management section needs to be re-written | Closed | Eng. Amr Helal | 2022-05-05
F_REVIEW_Audit_V1.0_016 | PMP | Eng. Amr Helal | Aml Nasser | 2022-05-05 | Our Team | Conf. management please add folder description | Closed | Eng. Amr Helal | 2022-05-05
F_REVIEW_Audit_V1.0_017 | PMP | Eng. Amr Helal | Aml Nasser | 2022-05-05 | Our Team | Naming convention needs more details | In Progress | Eng. Amr Helal | 2022-05-05 | Need to go deep in each branch
F_REVIEW_Audit_V1.0_018 | PMP | Eng. Amr Helal | Aml Nasser | 2022-05-05 | Our Team | no review comment from customer is added | Closed | Eng. Amr Helal | 2022-05-05
F_REVIEW_Audit_V1.0_019 | PMP | Eng. Amr Helal | Aml Nasser | 2022-05-05 | Our Team | Most of the review comments are still open | In Progress | Eng. Amr Helal | 2022-05-05 | Audit Comments will be Need Approval till the next Audit | Agreed
F_REVIEW_Audit_V1.0_020 | PMP | Eng. Amr Helal | Aml Nasser | 2022-05-05 | Our Team | how you will handle more than one review of PMP | Closed | Eng. Amr Helal | 2022-05-05 | Handled by review sheet We mention the version in the Review ID | Agreed
F_REVIEW_Audit_V1.0_021 | SRS | Eng. Amr Helal | Noura/Marina | 2022-05-05 | Our Team | only one version of SRS | Closed | Eng. Amr Helal | 2022-05-05
F_REVIEW_Audit_V1.0_022 | SRS | Eng. Amr Helal | Noura/Marina | 2022-05-05 | Our Team | empty revision history | Closed | Eng. Amr Helal | 2022-05-05
F_REVIEW_Audit_V1.0_023 | SRS | Eng. Amr Helal | Noura/Marina | 2022-05-05 | Our Team | only old document is uploaded | Closed | Eng. Amr Helal | 2022-05-05
F_REVIEW_Audit_V1.0_024 | GitHub | Eng. Amr Helal | Whole Team | 2022-05-05 | Our Team | empty revision history | Closed | Eng. Amr Helal | 2022-05-05
F_REVIEW_Audit_V1.0_025 | GitHub | Eng. Amr Helal | Whole Team | 2022-05-05 | Our Team | only old document is uploaded | Closed | Eng. Amr Helal | 2022-05-05
F_REVIEW_Aduit_V1.3_0.26 | ERD | Eng. Mohamed Hassan | Whole Team | 2022-05-07 | Our Team | Update the version | Open
F_REVIEW_Aduit_V1.3_0.27 | USECASE | Eng. Mohamed Hassan | Whole Team | 2022-05-07 | Our Team | Update the version | Open
F_REVIEW_Aduit_V1.3_0.28 | SRS | Eng. Mohamed Hassan | Whole Team | 2022-05-07 | Our Team | Update the version | Open
F_REVIEW_Aduit_V1.3_0.29 | PMP | Hager Hany | Whole Team | 2022-05-07 | Our Team | version consistency with the review sheet and version history | Open

## Progress_Chart
PMP | Open | 0 | SRS | Open | 0
| Closed | 14 |  | Closed | 19
| In Progress | 0 |  | In Progress | 0
| Need Approval | 0 |  | Need Approval | 0
| Total | 14 |  | Total | 19
WireFrame_Review | Open | 2 | Risk Plan | Open | 0
| Closed | 17 |  | Closed | 6
| In Progress | 0 |  | In Progress | 0
| Need Approval | 0 |  | Need Approval | 0
| Total | 19 |  | Total | 6
sequence Diagrams | Open | 0 | Audit_Review | Open | 4
| Closed | 2 |  | Closed | 15
| In Progress | 0 |  | In Progress | 3
| Need Approval | 0 |  | Need Approval | 7
| Total | 2 |  | Total | 29