## Sheet1
The change | As-Is state | The future state | Impact of that change on people's roles | Impact of that change on project | Impact of that change on time | Level of impact
Two of the team members will have an exam on Wednesday 11th of May (Hager Nassar and Nora). So they will work 2 days only (Thursday and Friday) instead of 7 days. | Tasks are assigned to 5 of the team members including the project manager. And tasks of the current phase is scheduled on to be finished on time. | The team will have to adapt to change with minimum loss possible. Some of the tasks will be assigned to 3 team members and 2 tasks will be delivered in later phase in order not to stress the 3 team members. | Hager Nassar and Nora's tasks for the first 5 days of the week will be assigned equaly to 3 team members (Monica, Marina and Hager Hany). | This phase will be delivered with reduced functionality. 1-(Search for restraunt) functionality in home page will be implemented in the next phase. 2-(Login for admin) functionality will be implemented in the next phase. | Testing phase will include the two functionalities: "search for restraunt" and "Login for admin" so they will have to scheduled in the next phase first before Testing. | HIGH
The project manager (Aml) has left the project and a new one came (Monica). | Amal nasser is the project manager. She understands the project and what the customer needs. She knows the team's abilities and areas of specialty and accordingly assigns the tasks. | A new project manager will overtake the project and manages the team, customer and the tasks. | The team members will have to set meetings to communicate the project state and functionalities to the project manager to make him understand the project and the customer's vision. | Current phase (Development) will be delivered with reduced functionalities. "search for restraunt" and "Login for admin" will be delivered in the next phase. | The increased meetings with the project manager will take place at the start of the week in the project schedule and some functionalities will be shifted to the next phase. | HIGH
Add Admin' and 'Add User' functionalities is removed as per the customer's request. | Add Admin' and 'Add User' are from the admin functionalities that the customer demanded. | Add Admin' and 'Add user' functionalities will be removed from all the system documents and middleware. | The team members will be assigned on trello to remove the functionalities from the SRS, Use case, Sequence diagrams and disable it from the middleware. | The functionalities will be removed from the SRS, Use case, Sequence diagrams and diabled from the middleware. | Time of testing will be reduced as the effort of testing of those functionalities is removed. | MEDIUM
Search for resdtraunt' functionality is asked by the project manager to be removed and the customer confirmed. | Search for restraunt' is from the user functionalities that the customer demanded. | Search for restraunt' functionality will be removed from all the system documents and middleware. | The team members will be assigned on trello to remove this functionalitity from the SRS, Use case, Sequence diagrams and disable it from the middleware. | The functionality will be removed from the SRS, Use case, Sequence diagrams and diabled from the middleware. | Time of testing will be reduced as the effort of testing of this functionalitity is removed. | MEDIUM
Author: Marina Hatem
Date created: 13.5.2022
Version: 1.0