## F_MenuItem
ID | Title | Description | Preconditions | Test Steps | Test Data | Expected Results | Actual Results | Status | Priority (Low/Medium/High) | Severity(Low/Minor/Major/Critical) | Detected by | Assigned to | Date | Comments
Bug_F_MenuItem_001 | QuantityField | Quantity Filed should't accept zero value as input | - logged in Successfully. | - After logging in successfully. - Select a restaurant from the home page. - in the menu page enter zero in the quantity field - Click on Confirm order | -restaurant MAC - quantity =0 | a pop up message will appear saying “ No meals have been selected” and stay in the menu page. | Zero input is accepted and user is directed to Confirmation Page. | Open | High | High | Monica | Hager Hany | 2022-05-27

## F_ConfirmationPage
ID | Title | Description | Preconditions | Test Steps | Test Data | Expected Results | Actual Results | Status | Priority (Low/Medium/High) | Severity(Low/Minor/Major/Critical) | Detected by | Assigned to | Date | Comments
Bug_F_ConfirmaOrder_001 | Submit Button | A pop Message Should apper saying “Order Confirmed and X points are added”. | -SignIn | -select Restaurant -enter the quantity of the menu item -Click on Confirm Button | _____ | a pop-up message will appear saying “Order Confirmed and X points are added”. | No pop up message and user Redirected to user homePage | Open | Medium | Minor | Monica | Monica | 2022-05-27
Bug_F_ConfirmaOrder_002 | Check on loyality points | Loyality points calculated wrong after using loyality points button | TC_F_ConfirmOrder_009 | -ViewOffers -select offer -go to the menu item page of the chosen restaurant offer -enter quantity of meal -press confirm -check the discount amount = amount offer selected -ViewOffers -check loyality points increased by order total price/4 | -select KFC 50 LE offer -Quantity=1 | discount amount =50 loyality points=50.625 | discount amount =50 loyality points=55 | Open | High | Major | hager | Monica | 2022-05-27

## F_AddRestaurants_Admin
ID | Title | Description | Preconditions | Test Steps | Test Data | Expected Results | Actual Results | Status | Priority (Low/Medium/High) | Severity(Low/Minor/Major/Critical) | Detected by | Assigned to | environment specifications | Date | Comments
Bug_F_AddMenuItem_Admin_001 | Add Menu Item | The Menu item page accepted empty Price field | 1-add restaurant succefully and redirected to Add menu item page | 1-click on "choose file" button 2- choose "x.png" 3-click open 4-Enter item name 5-Enter item price 6-Click on "Add" button | file name="x.png" item name="" item price="85" | "error message will appear below the item name field saying ” this field is required. " | Page loads and accepts the empty field. | Open | Medium | Minor. | Hagar EL-Sayed | Noura Amr | - Operating system: "windows 10" - Browser:"Google chrome" | 2022-05-27
Bug_F_AddMenuItem_Admin_002 | Add Menu Item | The admin accepted a blank item price field in add Menu | 1-add restaurant succefully and redirected to Add menu item page | 1-click on "choose file" button 2- choose "x.png" 3-click open 4-Enter item name 5-Click on "Add" button | file name="x.png" item name="Gourmet" item price="" | "error message will appear below the item price field saying ” this field is required. " | The system accepts the menu item with emty item price field. | Open | High | Major | Hagar EL-Sayed | Noura Amr | - Operating system: "windows 10" - Browser:"Google chrome" | 2022-05-27
Bug_F_AddMenuItem_Admin_003 | Add Menu Item | The add item form accepted to add an item without an image. | 1-add restaurant succefully and redirected to Add menu item page | 1-Enter item name 2-Enter item price 3-Click on the "Add" button | item name="Gourmet" item price="85" file name="" | "error message will appear below the choose file button saying ” No file selected. " | The menu item is accepted. | Open | Medium | Minor. | Hagar EL-Sayed | Noura Amr | - Operating system: "windows 10" - Browser:"Google chrome" | 2022-05-27
Bug_F_AddMenuItem_Admin_004 | Add Resturant | The error message mentioned "Menu item image" instead of "Restaurant logo" | 1-access Add restaurant page successfully | 1-Enter restaurant name 2-click on "choose file" button 3- chose "word .docx" 4-click open 5-click Add button | 1-Resturant name = " Mince" 2-file name=" word .docx" | an error message will appear that ”Restaurant logo must be JPG , JPEG or PNG extension ” | an error message appears that ”Menu item image must be JPG , JPEG or PNG extension ” | Open | Low | Low | Hagar EL-Sayed | Noura Amr | - Operating system: "windows 10" - Browser:"Google chrome" | 2022-05-27
Bug_F_AddMenuItem_Admin_005 | Add Menu Item | The add Menu Item accepted empty fields and take no action. | 1-add restaurant succefully and redirected to Add menu item page | 1-click Add button | item name="" item price="" file name="" | 1- "error message will appear below the choose file button saying ” No file selected. " 2- "error message will appear below the item name field saying ” This field is required. 3- "error message will appear below the item price field saying ” This field is required. " | Nothing happens. | Open | High | Major | Hagar EL-Sayed | Noura Amr | - Operating system: "windows 10" - Browser:"Google chrome" | 2022-05-27
Bug_F_AddMenuItem_Admin_006 | Add Resturant | The error message mentioned "Menu item image" instead of "Restaurant logo" | 1-access Add restaurant page successfully | 1-Enter restaurant name 2-click on "choose file" button 3- chose "text.txt" 4-click open 5-click Add button | 1-Resturant name = " Mince" 2-file name="text.txt" | an error message will appear that ”Restaurant logo must be JPG , JPEG or PNG extension ” | an error message appears that ”Menu item image must be JPG , JPEG or PNG extension ” | Open | Low | Low | Hagar EL-Sayed | Noura Amr | - Operating system: "windows 10" - Browser:"Google chrome" | 2022-05-27
Bug_F_AddRestaurant_Admin_007 | Add Resturant | The Add restaurant didn't accept name with spaces in the restaurant name | 1-access Add restaurant page successfully | 1-Enter restaurant name 2-click on "chose file" button 3-choose file "x.png" 4-click open 5-click Add button | 1- Resturant name ="beanos Cafe" 2-file name="x.png" | Admin is redirected to Add menu item page successfully | an error message will appear below the restaurant name field saying "Restaurant Name must be characters only” | Open | Medium | Minor | Hagar EL-Sayed | Noura Amr | - Operating system: "windows 10" - Browser:"Google chrome" | 2022-05-27
Bug_F_AddMenuItem_Admin_008 | Add Menu Item | The item name field in Menu Item did not accept space. | 1- Add restaurant successfully 2- access Add restaurant page successfully | 1-click on "choose file" button 2- choose "x.png" 3-click open 4-Enter item name 5-Enter item price 6-Click on "Add" button | 1-file name="x.png" 2-item name ="Beanos cafe" 3-item price="85" | pop up must appear saying “Add Successfully” | an error message appeared below the item name field saying "Enter a valid item name” | Open | Medium | Minor | Hagar EL-Sayed | Noura Amr | - Operating system: "windows 10" - Browser:"Google chrome" | 2022-05-27
Bug_F_AddRestaurant_Admin_009 | Add Resturant | system crashed when the admin add restaurant without menu item | 1-login as user | 2- click on marina restuarant | "1- Resturant name =""marina"" 2-file name=""x.png"" " | user will be redirected to menu item page and an empty menu item for marina restaurant should appear | system crashed | Open | High | critical | noura | Monika | - Operating system: "windows 10" - Browser:"Google chrome" | 2022-05-27